|  |  |  |  |
| --- | --- | --- | --- |
| Task List | Start Date | End Date | Status |
| Agreement Sign | 03/15/18 | 03/15/18 | Done |
| UI Concept | 03/15/18 | 03/18/18 | Done |
| System Architecture Design | 03/18/18 | 03/25/18 | Done |
| Initial UI Design | 03/21/18 | 04/05/18 | In Progress |
| Login page | 03/21/18 | 03/22/18 |  |
| Dashboard | 03/22/18 | 03/24/18 |  |
| Resource Upload page | 03/25/18 | 03/27/18 |  |
| Global Search Result page | 03/28/18 | 03/29/18 |  |
| Advance Search Page | 03/31/18 | 04/03/18 |  |
| SRS Document create | 03/25/18 | 04/05/18 | In Progress |
| Deployment to the Test Server | 04/03/18 | 04/05/18 |  |
| Core Functional Development | 04/05/18 | 05/19/18 |  |
| Database Design | 04/05/18 | 04/08/18 |  |
| User Management | 04/07/18 | 04/09/18 |  |
| Login Page | 04/08/18 | 04/09/18 |  |
| Uploading video content | 04/10/18 | 04/16/18 |  |
| Single file uploading | 04/10/18 | 04/10/18 |  |
| Transcoding video file | 04/11/18 | 04/14/18 |  |
| Batch file Uploading | 04/11/18 | 04/12/18 |  |
| Transcoding Batch video files | 04/15/18 | 04/16/18 |  |
| UAT | 04/17/18 | 04/17/18 |  |
| Uploading Audio Content | 04/17/18 | 04/21/18 |  |
| Single & Batch file | 04/17/18 | 04/19/18 |  |
| Audio file encoding | 04/19/18 | 04/21/18 |  |
| UAT | 04/22/18 | 04/22/18 |  |
| Upload Image & Document | 04/22/18 | 04/23/18 |  |
| Single & Batch file | 04/22/18 | 04/23/18 |  |
| Smart Search | 04/24/18 | 04/28/18 |  |
| Advance Search | 04/26/18 | 04/30/18 |  |
| Search Result page |  |  |  |
| Preview, Edit & Delete action | 05/01/18 | 05/05/18 |  |
| UAT | 05/06/18 | 05/06/18 |  |
| Dashboard | 05/06/18 | 05/08/18 |  |
| Role based Permission Management | 05/08/18 | 05/14/18 |  |
| UAT | 05/15/18 | 05/15/18 |  |
| Testing & Bug Fixing | 05/16/18 | 05/19/18 |  |
| Final Demo | 05/20/18 | 05/20/18 |  |
| UAT | 05/21/18 | 06/04/18 |  |
| Deployment to the Main server | 06/05/18 | 06/07/18 |  |
| Data Collection & Upload | 06/09/18 | 06/24/18 |  |
| Final Delivery | 03/15/18 | 06/25/18 |  |